## Slide 1
OPS5 Progress Report
Carlo Carugi
Senior Evaluation Officer
Abuja. October 1-3, 2013

## Slide 2: Setting the Stage
Progress Report requested by first replenishment meeting
This report will “flag issues” that need to be taken up in the replenishment on the basis of ongoing work for OPS5
In addition: first impression of how recommendation of first report is taken up (on MFA and on broader adoption)
In addition: performance issues emerging as problematic, whereas GEF-6 proposals do not yet fully discuss these

## Slide 3: Issues
Portfolio
Programming
Impact
Performance/project cycle
Results based management
Work in progress

## Slide 4: Portfolio
Further analysis of multi-focal area projects (MFA)
102 projects with multi-focal objectives but not approved as MFA were added to analysis
Total MFA: 17% of projects and 22.5% of funding (47% in GEF-5)
Analysis on “integrated” versus “non-integrated” MFA activities in projects

## Slide 5: MFA portfolio
MFA projects have same percentage of moderately satisfactory and higher outcome ratings as single focal area projects (FA)
But if we look only at satisfactory and highly satisfactory ratings, FAs score higher
This may be indicative for the relative complexity of MFAs
MFAs with integrated activities score better on sustainability than MFAs with “bundled” activities
M&E of MFAs scores lower than M&E of FAs

## Slide 6: MFA issues
MFAs have potential to effectively and sustainably address connected focal area issues through integrated activities
The M&E burden on MFAs, as noted in several country portfolio evaluations, is confirmed and should be addressed
MFAs do not receive much attention in the GEF-6 proposals

## Slide 7: Programming
International funding of environmental support has doubled from 2007 to 2011
GEF has benefited from this, but with a relatively lower increase

## Slide 8
Available global public funding> $ 10 billion
Public spending on over-use of resources> $ 1 trillion
Global public funding needs> $ 100 billion

## Slide 9: Issue 1
Expectations for GEF-6 are not as positive as they were for GEF-5
Proposals for GEF-6 double the number of program level objectives in focal areas, in set-asides and in corporate programs compared to GEF-5
Potential underfunding of focal areas, countries and/or modalities of the GEF needs to be discussed and taken into account when considering programming for GEF-6

## Slide 10: NPFE mid-term evaluation
Report will be presented to Council in November
Three issues emerge for the 2nd replenishment meeting:
  NPFEs were highly relevant to countries
  Actual programming was –with exceptions– unsuccessful
  Implementation of the support was highly inefficient

## Slide 11: NPFE relevance
Support for programming helps address the “pre-project cycle phase” that often remains a black box
While the programming itself often was unsuccessful, it has helped countries set up better mechanisms for coordination and future programming
Stakeholder involvement increased in several NPFE countries

## Slide 12: NPFE effectiveness
Only a limited number of projects identified during NPFEs were approved
Many project concepts were not eligible for GEF support
Concepts not commensurate with funding levels
Other priorities took over after the NPFE

## Slide 13: NPFE efficiency
Long initial time delays due to choice of modality
Lack of guidance on eligibility and funding levels
Shifts in guidance, one in defiance of Council decision
  Shift: countries were not allowed to enter PIFs if NPFE had not been finished, despite Council request that they should be able to do so

## Slide 14: Issue 2
Programming of GEF support to countries and regions will remain crucial in GEF-6 and support for this should continue
A revised NPFE could include priority setting for regional issues
Follow-up to Expanded Constituency Workshops could play a role
Timing should be at end of GEF period, not at the start of a new period

## Slide 15: Impact
Request of first replenishment meeting to provide further analysis on broader adoption
Larger cohort of projects studied
Analysis focused on crucial factors that speed up progress toward impact
More nuanced analysis to provide greater insight
New MFA cohort not yet fully integrated, so more work will need to be done for the final report of OPS5!

## Slide 16: Impact in First Report
Four mechanisms for broader adoption identified
Mainstreaming and replication tend to lead to slower broader adoption than up-scaling and market change
This means projects should include design elements that initiate up-scaling and market change
GEF-6 focal area proposals (doc. I) seem to prefer mainstreaming and replication
This may be an issue of terminology, but it may also lead to project proposals that focus less on broader adoption

## Slide 17: Broader Adoption
Mainstreaming: Information, lessons, or specific results of the GEF are incorporated into broader stakeholder mandates and initiatives such as laws, policies, regulations, and programs
Replication: GEF-supported initiatives are reproduced or adopted at a comparable administrative or ecological scale, often in another geographical area or region
Scaling-up: GEF-supported initiatives are implemented at a larger geographical scale, often expanded to include new aspects or concerns that may be political, administrative, or ecological in nature
Market change: GEF-supported initiatives catalyze market transformation by influencing the supply of and/or demand for goods and services that contribute to global environmental benefits

## Slide 18: Definitions of Impact
Positive and negative, primary and secondary long-term effects produced by an intervention, directly or indirectly, intended or unintended (OECD/DAC)
Environmental impact: changes in biophysical parameters
Direct impact: changes attributable to an intervention
Long term impact: changes emerging over time in long duration biophysical processes
Impact scales go from single sites to system-level impact
Globally significant impacts have local impact as well, but not all local impact is globally significant
Social and economic impacts are essential to achieve environmentally sustainable development
Text box 1

## Slide 19: Overview of Impact Cohort
Chart: 
| BD | CC | IW | LD | MF | OD | PP
NO. OF PROJECTS | 234 | 113 | 58 | 20 | 33 | 5 | 10
% | 0.495 | 0.239 | 0.123 | 0.042 | 0.07 | 0.011 | 0.021
FOCAL AREA | NO. OF PROJECTS
BD | 234
CC | 113
IW | 58
LD | 20
MF† | 33
OD | 5
PP | 10
Grand Total | 473*
*18 projects excluded from OPS4 & OPS5 cohorts due to unavailable TEs or insufficient information in TEs
†includes only projects approved as multi-focal, not projects implemented as such under individual focal areas

## Slide 20: Broader Adoption at Project Completion
Chart: 
| BD | CC | IW | LD | MF | OD | PP | Total
Most broader adoption initiatives adopted/ implemented | 0.175 | 0.142 | 0.172 | 0 | 0.152 | 0.2 | 0 | 0.154
Some broader adoption initiatives adopted/ implemented | 0.419 | 0.522 | 0.569 | 0.25 | 0.182 | 0.4 | 0.1 | 0.431
Some broader adoption initiated | 0.333 | 0.239 | 0.172 | 0.55 | 0.364 | 0.4 | 0.5 | 0.307
No significant broader adoption taking place | 0.073 | 0.097 | 0.086 | 0.2 | 0.303 | 0 | 0.4 | 0.108
Notes: Extent of broader adoption, by % of projects per focal area. * Add DARKEST and DARKER RED for total no. of projects with broader adoption initiatives successfully adopted/ implemented. FINDINGS: 1) 59% of all projects had broader adoption initiatives adopted/ implemented, 31% had mostly broader adoption initiatives that were initiated or planned but not implemented, and 11% had either unsuccessful or no broader adoption initiatives. 2) IW had the greatest % of projects (74%) with broader adoption initiatives adopted/ implemented, followed by CC (66%), then OD (60%) and BD (59%). All other focal areas had less than 50% of projects with broader adoption initiatives adopted/ implemented.

## Slide 21: Mechanisms for Broader Adoption
Chart: 
| Management frameworks/ approaches | Technologies/ infrastructure | Financial Mechanisms | Management systems | Laws/ Policies/ Regulations | Government structures | Mechanisms/processes for participation & trust-building/conflict resolution
Mainstreaming | 0.25793 | 0.15856 | 0.16702 | 0.21776 | 0.43129 | 0.23679 | 0.1945
Replication | 0.090909 | 0.067653 | 0.035941 | 0.033827 | 0.0021142 | 0.0042283 | 0.012685
Scaling-up | 0.052854 | 0.010571 | 0.010571 | 0.014799 | 0.019027 | 0.021142 | 0.0042283
Market Change | 0.012685 | 0.035941 | 0.040169 | 0.0042283 | 0.014799 | 0 | 0.0021142
Notes: N=473. FINDINGS: 1) The most commonly adopted types of interventions are laws/ policies/ regulations (47%) followed by management frameworks/ approaches (41%). 2) The most common form of broader adoption initiatives adopted/ implemented is the mainstreaming of laws/ policies/ regulations (42%). 3) For broader adoption mechanisms other than mainstreaming, the types of interventions most commonly seeing broader adoption are Implementing Strategies. 4) For most projects, the interventions take place either at site or national level and is broadly adopted at the same scale. For scaling-up and market change, the most broadly adopted interventions begin at the site and are adopted at the national scale.

## Slide 22: Broader Adoption and Environmental Impact
Chart: 
| Most broader adoption initiatives adopted/ implemented | Some broader adoption initiatives adopted/ implemented | Some broader adoption initiated | No significant broader adoption taking place
With Environmental Impact | 62 | 124 | 67 | 8
No Environmental Impact | 7 | 48 | 55 | 17
No. of Projects
90%
10%
Notes: TOTAL N=401, projects where stress reduction can be expected. ENVIRONMENTAL IMPACT = Moderate + High Stress Reduction + Improved Environmental Status, n=262; NO ENVIRONMENTAL IMPACT = Insignificant + None, n=139. EXTENT OF BROADER ADOPTION: Most broader adoption initiatives adopted/ implemented, n=69; Some broader adoption initiatives adopted/ implemented, n=172; Some broader adoption initiated, n=122; No significant broader adoption taking place, n=38 .
FINDINGS: 1) 46% of projects that can be expected to result in stress reduction have both successful broader adoption and environmental impact. 2) 21% of projects have neither environmental impact or progress in broader adoption 3) Projects where broader adoption initiatives have been adopted/ implemented have a much higher % of projects with environmental impact (77%), while those with no broader adoption have a higher % of projects that do not have environmental impacts (53%). 4) 55% of projects that have some broader adoption initiated/ planned 17% of total projects) have environmental impact while 45% (14% of total projects) have no environmental impact.

## Slide 23: Factors Affecting Progress Towards Impact
 | CONTRIBUTING FACTORS | HINDERING FACTORS
PROJECT-RELATED | Good engagement of stakeholders Highly relevant technology/approach Broader adoption processes initiated using project resources | Poor project design No activities to sustain project outcomes
CONTEXTUAL | Country support Previous/current related initiatives (by government, global events, etc.) Other stakeholder support | Other unfavorable political/ policy conditions/events Unfavorable economic conditions/events/ drivers Lack of country support
Notes: N=473. Factors affecting most projects, regardless of extent of broader adoption. Poor project design: wrong assumptions about risks, government cooperation & stakeholder needs, overly ambitious objectives, no M&E to provide sufficient information. No activities to sustain momentum: lack of resources or activities related to broader adoption. Other unfavorable political/ policy conditions/events: political power changes, civil unrest, no tenure rights, country priorities and programs not aligned or in conflict with project objectives. Unfavorable economic conditions/events/ drivers: no market demand for environmental solutions, higher demand for goods and industries not aligned or in conflict with project objectives. Lack of country support: no political will, law enforcement or funds allocated to support initiatives at either national or local level. Other stakeholder support: e.g. donors, private sector, local communities.
FINDING: 1) Hindering factors affecting most projects are due to drivers beyond the project’s control.

## Slide 24: From Immobility to Progress
More successful
Poor project design
No activities to sustain project outcomes
Lack of country support
Broader adoption processes initiated using project resources
Other stakeholder support
EXTENT OF BROADER ADOPTION
Less successful
Chart: 
| Poor project design | No activities to sustain momentum | Lack of country support | Other stakeholder support (e.g. donors, private sector) | Broader adoption processes initiated using project resources
LESS SUCCESSFUL | -0.49 | -0.37 | -0.38
MORE SUCCESSFUL | 0.51 | 0.51
Notes: % of projects within extent of broader adoption. More successful= Most + some broader adoption initiatives adopted/ implemented, n=277; Less successful= Some broader adoption initiatives initiated + no significant broader adoption taking place, n=196. NOTE: 31% of less successful projects have some broader adoption planned or initiated *Contextual factors in gray and italics. Poor project design: wrong assumptions about risks, government cooperation & stakeholder needs, overly ambitious objectives, no M&E to provide sufficient information. No activities to sustain momentum: lack of resources or activities related to broader adoption. Lack of country support: no political will, law enforcement or funds allocated to support initiatives at either national or local level. Other stakeholder support: e.g. donors, private sector, local communities. See raw tables for comparative differences in % of more successful vs. less successful.

## Slide 25: Factors Affecting Progress Toward Impact at Project Completion
 | CONTRIBUTING FACTORS | HINDERING FACTORS
PROJECT-RELATED | Good engagement of stakeholders Highly relevant technology/approach Broader adoption processes initiated using project resources | Poor project design No activities to sustain project outcomes
CONTEXTUAL | Country support Previous/current related initiatives (by government, global events, etc.) Other stakeholder support | Other unfavorable political/ policy conditions/events Unfavorable economic conditions/events/ drivers Lack of country support
REALM OF GEF CONTROL
Notes: N=473. Factors affecting most projects, regardless of extent of broader adoption. Poor project design: wrong assumptions about risks, government cooperation & stakeholder needs, overly ambitious objectives, no M&E to provide sufficient information. No activities to sustain momentum: lack of resources or activities related to broader adoption. Other unfavorable political/ policy conditions/events: political power changes, civil unrest, no tenure rights, country priorities and programs not aligned or in conflict with project objectives. Unfavorable economic conditions/events/ drivers: no market demand for environmental solutions, higher demand for goods and industries not aligned or in conflict with project objectives. Lack of country support: no political will, law enforcement or funds allocated to support initiatives at either national or local level. Other stakeholder support: e.g. donors, private sector, local communities.
FINDING: 1) Hindering factors affecting most projects are due to drivers beyond the project’s control.

## Slide 26: Issue 3
Project design issues hindered 74% of less successful projects
These projects were also more susceptible to negative contextual conditions
Projects that engage stakeholders and that include activities to broader adoption during implementation tend to fare well despite unfavorable contextual conditions
Project design and implementation should ensure engagement of stakeholders and allocation of resources towards activities supporting broader adoption
A community of practice on broader adoption could bring together country and agency experiences and include expertise from STAP, the Evaluation Office and the Secretariat
Notes: N=473. More successful= Most + some broader adoption initiatives adopted/ implemented; n=277 ; Less successful = Some broader adoption initiatives initiated + no significant broader adoption taking place, n=196. ADDITIONAL FINDING: Only 19% of LESS SUCCESSFUL projects considered CONTEXTUAL factors as most significant in hindering progress.

## Slide 27: Performance
Project cycle: analysis has now moved from September 30 2012 to include June 30 2013
Final report will go to September 30, 2013
Indicative finding: standard of 18 months from Council approval to CEO endorsement is not met for more than 50% of FSPs
Further analysis is done for reasons why
Replenishment should discuss project cycle issues at its third meeting in December

## Slide 28: Less than 50%...

## Slide 29: But FSPs under programmatic approaches seem to go faster…

## Slide 30: Issue 4
The reasons for the failure to meet the 18 month standard are still subject of further analysis
The Secretariat in its responses to PIFs and CEO endorsement requests has been timely; other factors are being explored
The project cycle remains slow and cumbersome and will need to become an issue for discussion in the third replenishment meeting, when the final analysis of OPS5 is available

## Slide 31: RBM & M&E
GEF-5 increased the number of goals, objectives, targets, indicators and tracking tools
Compliance with monitoring requirements has gone down over GEF-4 and GEF-5
  M&E ratings are slowly decreasing
  Data generated through GEF support are not always institutionally safeguarded or available
The cost of monitoring increases if many indicators and targets are adopted – M&E budgeting may not have been sufficient
RBM and monitoring need to find the right balance between funding for operations and funding for data gathering and analysis

## Slide 32: RBM and monitoring issue
No assessment of costs and benefits of adequate monitoring of the full list of GEF-5 indicators was presented to the fifth replenishment
Ongoing work on tracking tools puts a question mark on the completeness and reliability of the data reported in AMR part 2
The GEF may want to measure too much in too great a detail

## Slide 33: GEF-6 increasing the burden?
The GEF-6 proposals present a significant increase in goals, objectives, programs and components
SGP as example: it is proposed to introduce 4 programs within SGP, whereas in GEF-5 SGP had no sub-programs
The on-going joint evaluation of SGP indicates that M&E and RBM in SGP is unrealistic; adding programs will potentially inflate the problem
The first phase findings will become available shortly and could be taken up

## Slide 34: Issue 5
The GEF should consider reducing the burden of targets, indicators and tracking tools and reform its results based management system accordingly, so that what gets measured gets measured better, more reliable and more consistent

## Slide 35: Work in Progress
Adaptation
Gender
CSO engagement
Private Sector engagement
STAP
Health of the Network
Knowledge Management
Co-financing

## Slide 36
Thank you
ops5@thegef.org
www.gefeo.org