## Slide 1: GEF Financing & Project Cycle
GEF Expanded Constituency Workshop
Minsk, Belarus
September 22-24, 2015

## Slide 2
Full-Sized Projects (FSPs): GEF financing > $2 million
Medium-Sized Projects (MSPs): GEF financing < $2 million
Enabling Activities (EAs): max. financing per reporting determined by relevant Convention
  Project Preparation Grants (PPGs)
Small Grants Program: max. $50K
GEF Financing Schemes
Project Amount (up to) | 1M | 3M | 6M | 10M
Max. PPG amount | 50K | 100K | 150K | 300K
Biodiversity | Climate Change | Land Degradation | Chemicals & Waste | 
CBD | UNFCCC | UNCCD | Minamata | POPs
Nat’l BD Strategies & Action Plan | Nat’l Communications |  | Mercury Initial Assessment | Nat’l Implementation Plan
6th Nat’l Report to CBD | Biennial Update Report |  | Artisanal & Small Scale Gold Mining Nat’l Action Plan | 
3rd Nat’l Report to Cartagena Protocol |  |  |  | 

## Slide 3
GEF Council and Secretariat
Step 1: Council approval of Work Program (consisting of PIFs cleared by the CEO)
Step 2: CEO endorsement of project
GEF Agency
Step 3: Agency’s internal approval of project
Step 4: Project implementation (project completion follows terminal evaluation and financial closure)
Full-Sized Project Cycle
STEP 1
GEF COUNCIL approval of Work Program
STEP 2
GEF CEO endorsement of project
STEP 3
AGENCY approval of project
STEP 4
AGENCY project implementation

## Slide 4
Preferred for MSP
GEF Secretariat
Step 1: CEO approval of Final MSP request (w/PPG request, if needed) & Project document
GEF Agency
Step 2: Agency internal approval
Step 3: Project implementation
Medium-Sized Project & Enabling Activity Cycle
One-Step Approach
STEP 1
GEF CEO approval of Final MSP
STEP 2
AGENCY approval of MSP
STEP 3
AGENCY project implementation

## Slide 5
GEF Secretariat
Step 1: CEO approval of MSP project concept (PIF) submission (w/PPG request, if needed)
Step 2: CEO approval of Final MSP request and project document
GEF Agency
Step 3: Agency internal approval
Step 4: Project implementation
Medium-Sized Project Cycle
Two-Step Approach (only if required)
STEP 1
GEF CEO approval of MSP Concept (PIF)
STEP 2
GEF CEO approval of FINAL MSP
STEP 3
AGENCY approval of project
STEP 4
AGENCY project implementation

## Slide 6
GEF Council and Secretariat
Step 1: Council approval of Work Program (consisting of PFDs cleared by the CEO)
Step 2: Council review of Child Project (only for IAPs)
Step 3: CEO endorsement of Child Project
GEF Agency
Step 4: Agency’s internal approval of project (which signifies start of project implementation)
Step 5: Project implementation (project completion follows terminal evaluation and financial closure)
Programmatic Approach Cycle
STEP 1
GEF COUNCIL approval of Work Program
STEP 2
GEF COUNCIL review of Child Project
STEP 4
AGENCY approval of Child Project
STEP 5
AGENCY project implementation
STEP 3
GEF CEO endorsement of Child Project

## Slide 7
Country Operational Focal Point (OFP)’s endorsement letter is the evidence of approval for using the country STAR resources and a key requirement for:
  PIFs (FSPs) to enter the Work Program
  PFDs (PAs) to enter the Work Program
  MSP Requests for CEO approval
  EA Requests for CEO approval
  PPG Requests (often accompanied with baseline projects)
Note: Biodiversity, climate change, and land degradation focal area projects are subject to STAR resources.
Country Endorsement

## Slide 8: System for Transparent Allocation of Resources: STAR

## Slide 9
The current mechanism by which GEF resources are allocated to countries in three focal areas – Biodiversity, Climate Change, and Land Degradation
The Resource Allocation Framework (RAF) was the first PBA for the GEF and adopted for GEF-4
The STAR updated the RAF and was implemented for GEF-5
The STAR was recently updated for GEF-6
Background

## Slide 10
STAR aims to allocate scarce GEF resources within and among focal areas in order to:
  maximise impact on the global environment
  promote sound environmental policies and practices
  meet convention requirements
  match country driven priorities
Objectives

## Slide 12
1
Determine Available Focal Area Funds
2
Calculate “Country Scores”
3
Calculate Preliminary Country Allocations
4
Adjust for Floors and Ceilings
5
Obtain Final Allocations
6
Determine post-allocation Flexibilities
Calculating STAR allocations

## Slide 13
Total Envelope
Focal Areas
less Set Asides
Country Allocations
STAR Focal Areas
Available Focal Area Funds

## Slide 14
1
Determine Available Focal Area Funds
2
Calculate “Country Scores”
3
Calculate Preliminary Country Allocations
4
Adjust for Floors and Ceilings
5
Obtain Final Allocations
6
Determine post-allocation Flexibilities
Calculating STAR allocations

## Slide 15
Global Benefits Index: measures a country’s relative share of GEF potential benefits that can be generated by a fixed amount of resource input into a focal area
Country Performance Index: measures a country’s performance and capacity to deliver potential global environmental benefits ***************
GDP Index: designed to increase allocation of countries with a low GDP per capita
The main indices

## Slide 16
COUNTRY SCORE
Global Benefits Index
Country Performance Index
GDP Index
Biodiversity
Climate Change
Land Degradation
Country Score = GBI0.8 CPI 1.0 GDP-0.08
The country score

## Slide 17
1
Determine Available Focal Area Funds
2
Calculate “Country Scores”
3
Calculate Preliminary Country Allocations
4
Adjust for Floors and Ceilings
5
Obtain Final Allocations
6
Determine post-allocation Flexibilities
Calculating STAR allocations

## Slide 18
Country Share =
Country Score / Sum of Country Scores for all eligible countries
Preliminary Allocation =
Country Share * Available Focal Area Funds
Preliminary country allocations

## Slide 19: Approximate Calculation: Trinidad and Tobago
 | BIODIVERSITY | CLIMATE CHANGE | LAND DEGRADATION
GBI | 0.21 | 0.12 | 0.30
CPI | 3.65 |  | 
GDPI | 17934.06 |  | 
COUNTRY SCORE (GBI0.8 CPI 1.0 GDP-0.08) | 0.48 | 0.306 | 0.63
SUM OF COUNTRY SCORES | 174.45 | 147.30 | 189.39
COUNTRY SHARE | 0.002753 | 0.00208 | 0.00333
FOCAL AREA ALLOCATION | 1051 | 941 | 346
PRELIMINARY COUNTRY ALLOCATION | 2.89 | 1.96 | 1.15
FINAL COUNTRY ALLOCATION | 2.78 | 2.29 | 1.14
TOTAL ALLOCATION = 6.22 MILLION (FULLY FLEXIBLE COUNTRY) |  |  | 

## Slide 20
1
Determine Available Focal Area Funds
2
Calculate “Country Scores”
3
Calculate Preliminary Country Allocations
4
Adjust for Floors and Ceilings
5
Obtain Final Allocations
6
Determine post-allocation Flexibilities
Calculating STAR allocations

## Slide 21
Focal Area | Floor for LDCs | Floor for Non LDCs | Ceiling % | Ceilings (US Mn)
Climate Change | 3 | 2 | 10% | 126
Biodiversity | 2 | 1.5 | 10% | 129.6
Land Degradation | 1 | 0.5 | 10% | 43.1
Floors and Ceilings

## Slide 22
1
Determine Available Focal Area Funds
2
Calculate “Country Scores”
3
Calculate Preliminary Country Allocations
4
Adjust for Floors and Ceilings
5
Obtain Final Allocations
6
Determine post-allocation Flexibilities
Calculating STAR allocations

## Slide 23
Adjustments for floors and ceilings mean there is a surplus or deficit relative to the preliminary allocation
This is then allocated among countries using the country scores
Process iterates until the full amount has been allocated among countries
Final allocations

## Slide 24
1
Determine Available Focal Area Funds
2
Calculate “Country Scores”
3
Calculate Preliminary Country Allocations
4
Adjust for Floors and Ceilings
5
Obtain Final Allocations
6
Determine post-allocation Flexibilities
Calculating STAR allocations

## Slide 25
Flexibilities relate to the utilization(not allocation) of GEF resources
Countries are allowed to adjust their focal area allocations (but not their total envelope)
Total Allocation X | Allowed Marginal Adjustment
X ≤ 7 million | unlimited
X > 7 million | 2 million
Flexibilities and marginal adjustment

## Slide 26: Approximate Calculation: Trinidad and Tobago
 | BIODIVERSITY | CLIMATE CHANGE | LAND DEGRADATION
GBI | 0.21 | 0.12 | 0.30
CPI | 3.65 |  | 
GDPI | 17934.06 |  | 
COUNTRY SCORE (GBI0.8 CPI 1.0 GDP-0.08) | 0.48 | 0.306 | 0.63
SUM OF COUNTRY SCORES | 174.45 | 147.30 | 189.39
COUNTRY SHARE | 0.002753 | 0.00208 | 0.00333
FOCAL AREA ALLOCATION | 1051 | 941 | 346
PRELIMINARY COUNTRY ALLOCATION | 2.89 | 1.96 | 1.15
FINAL COUNTRY ALLOCATION | 2.78 | 2.29 | 1.14
TOTAL ALLOCATION = 6.22 MILLION (FULLY FLEXIBLE COUNTRY) |  |  | 

## Slide 28
Country | Flexible | Biodiversity | Climate Change | Land Degradation | Total
Armenia | FALSE | 1,500,000 | 2,000,000 | 4,398,159 | 7,898,159
Azerbaijan | FALSE | 1,500,000 | 4,841,274 | 3,218,297 | 9,559,571
Belarus | FALSE | 1,500,000 | 8,547,119 | 500,000 | 10,547,119
Kazakhstan | FALSE | 5,043,171 | 11,808,681 | 5,134,631 | 21,986,483
Kyrgyzstan | TRUE | 1,562,942 | 2,000,000 | 3,035,782 | 6,598,724
Russian Federation | FALSE | 25,434,939 | 60,574,033 | 8,185,815 | 94,194,787
Tajikistan | TRUE | 1,500,000 | 2,000,000 | 2,776,009 | 6,276,009
Turkmenistan | FALSE | 1,814,282 | 4,987,726 | 3,289,095 | 10,091,103
Uzbekistan | FALSE | 1,784,252 | 11,462,046 | 5,121,428 | 18,367,726
Notes: This slide is modified depending on the workshop

## Slide 29: Key GEF-6 Policies

## Slide 30
  Full-Sized Project Agency Fee : 40/60 tranche payment
  40% of the fee will be paid
  after Council approval of Work Program
  60% of the fee will be paid
  after CEO endorsement
ALL projects (FSPs, MSPs, EAs & PAs) |  | 
 | $10M & less | Over $10M
10 Existing Agencies | 9.5% | 9.0%
8 Project Agencies (GEF-6 Accreditation Pilot) | 9.0% (irrespective of project amount) | 
Fees for PPGs | Same rate as the baseline project | 
Small Grants Program | 4.0% | 
Agency Fee Policy

## Slide 31
Objectives:
to improve the GEF’s operational efficiency; ensure timely project preparation & processing
to deploy the GEF funding and resources effectively that GEF-financed projects remain relevant to the objectives & priorities of the recipient countries
Phased approach
  Exceptions: extraordinary events (i.e., extraordinary natural disaster/epidemic, war); If justified, Council will be notified.
  Cancelled projects may be resubmitted within a year (for FSP)/within 6 month (for MSP) for consideration of CEO endorsement/approval, if resources are available.
FSP PIF Council approval
12 month Notification to Agency & OFP
18 month Cancellation
MSP PIF CEO approval
6 month Notification to Agency & OFP
12 month Cancellation
Project Cancellation Policy

## Slide 32
  “Co-financing” definition:
  Resources that are additional to the GEF financing (determined on the basis of the agreed incremental cost principle) and that are provided by the GEF Partner Agency itself and/or by other non-GEF sources that support the implementation of the GEF-financed project and the achievement of its objectives.
  Co-financing is
  required for Full & Medium-sized Projects, Programmatic Approaches
  optional for Enabling Activities
  Required info for Co-financing: source, type (i.e., grant, loan, guarantee, in-kind) & amount
    Council Approval on Work Program (PIFs & PFDs): indicative info
    CEO Endorsement: confirmed info along w/proof of evidence (i.e., grant agreement)
Co-Financing Policy

## Slide 33
GEF and Gender Mainstreaming
“As the GEF moves forward with a new and innovative investment strategy, we are deeply committed to initiating and enhancing projects to more effectively deliver on the goals for gender equality while addressing the challenges we face on the global environment. These are not separate issues. Only by engaging partners, both women and men, can we reverse the negative trends threatening our ecosystems and save them for our future generation.”
Naoko Ishii, GEF CEO and Chairperson
Notes: The GEF recognizes the strong linkages between the achievement of global environmental benefits, gender equality, equity and social inclusion.

## Slide 34
  Gender & the Environment
  Women play an important role in managing and preserving biodiversity, water, land and other natural resources at the local scale.
  Environmental degradation has severe consequences for all human beings and particularly affects the most vulnerable, often women who constitute the majority of the world’s poor.
  Women's equal access to and control over resources not only improves the lives of individuals, families and countries, but also help ensure environmental sustainability.
  GEF’s Commitments to Gender Equality & Women’s Empowerment
  Gender equality is an important goal in the context of GEF operations - it helps to advance both the GEF’s objectives of attaining global environmental benefits and those related to gender equality, equity, and social inclusion:
  GEF 2020 Strategy
  GEF Policy on Gender Mainstreaming (2012)
  GEF Gender Equality Action Plan (2014)
Gender Equality Matters
Notes: The GEF recognizes the strong linkages between the achievement of global environmental benefits, gender equality, equity and social inclusion.
GEF commitment to gender equality is founded on the important understanding that gender equality is a social goal in and of itself, with associated implications for the GEF’s strategy, operations and procedures.
The GEF Gender Equality Action Plan (GEAP), approved by the GEF Council in 2014, commits the GEF Secretariat to enhance gender equality and women’s empowerment dimensions in its policies, programs, and projects.

## Slide 35
Gender Mainstreaming Policy (Agency Minimum Requirements)
Operational Level
Institutional capacity & framework for gender mainstreaming: Agency policy that requires to design and implement projects to ensure that both women & men (i) receive culturally compatible social and economic benefits, (ii) do not suffer adverse effects, and that (iii) fosters full respect for their dignity and human rights & Gender focal point
Gender responsive project cycle processes, incorporating socio-economic and gender aspects, including systems for monitoring and evaluating progress on gender mainstreaming.
Project Level
Social assessment, incl. gender analysis, to assess the potential roles, benefits, impacts and risks for women & men
Integration of specific measures to minimize or mitigate adverse gender impacts
Integration of gender sensitive activities
Gender responsive results-based framework including the use of project level gender disaggregated indicators
Engagement of gender & social experts
Notes: The GEF gender policy was initially developed in relation to the “accreditation” Policy, similar to fiduciary standards and safeguards. Moreover GEF commitment to gender equality is further founded on the important understanding that gender equality is an important social goal in and of itself, with associated implications for the GEF’s strategy, operations and procedures.

## Slide 36
Gender Equality Action Plan (GEAP)
  Project Cycle: Ensure gender-responsive GEF project cycle management processes & procedures, incl. development of guidelines for gender mainstreaming
  Policy & Programs: Mainstream gender considerations in key GEF policies & programs; support gender responsive projects based on country demand and GEF 6 Strategy
  Knowledge & Learning: Enhance & disseminate knowledge on gender equality & women’s empowerment related to the GEF strategy & project portfolio; facilitate knowledge exchange and visibility
  Results-based Management: Ensure GEF-wide accountability for gender mainstreaming by strengthening corporate & focal area level indicators to help track progress on gender mainstreaming
  Capacity Development: Strengthen capacity at GEF Secretariat & staff levels, OFPs & partners at country level
GEF Gender Partnership (2015)
Comprising of gender focal points from each GEF Agency, Convention Secretariats, Independent Evaluation Office, CSO Network & Indigenous Peoples Advisory Group
Serving as a platform and community of practice & knowledge broker to ensure meaningful and effective coordination of the implementation of the GEAP
Notes: Responding to the GEF-6 Policy Recommendation, the GEAP was developed in close consultation with the GEF Agencies, Convention Secretariats and other partner organizations to ensure coherence and accelerate progress at both corporate and focal area levels, including project cycle, knowledge and result-based management. GEAP builds on the existing and planned gender strategies and plans of the GEF Agencies and other partners
Priorities: 2015 -2016
Develop a guideline paper on mainstreaming gender in GEF projects
Compilation, exchange and advocacy of good practices, approaches and tools on gender mainstreaming among GEF Agencies and related organizations
Improve systems /procedures for monitoring and reporting on focal area and GEF-6 core gender indicators

## Slide 37: GEF-6 Core Gender Indicators
Outcome | Indicators | Verification
Gender-responsive project design | 1. Percentage of projects that have conducted gender analysis during project preparation 2. Percentage of projects that have incorporated gender responsive project results framework (e.g. gender responsive output, outcome, indicator, budget) | Project Document at CEO endorsement Have the project conducted a gender analysis? Does the project results framework include sex-disaggregated indicators?
Project implementation ensuring gender equitable participation in and benefits from project activities | 3. Share of women and men as direct beneficiaries of project 4. Share of convention related national reports incorporated gender dimensions (e.g. NBSAP, NAPA, TDA/SAP) (when applicable) | Project implementation reports, mid-term evaluation reports (GEF focal area tracking tools) Number direct beneficiaries disaggregated by gender
Project monitoring & evaluation giving adequate attention to gender mainstreaming | 5. Percentage of monitoring and evaluation report that incorporates gender equality/women’s empowerment issues and assess results | Project implementation reports, mid-term evaluation reports (GEF focal area tracking tools) Does midterm evaluation reports (or terminal reports) incorporate gender equality and woman's empowerment issues and assess results ?
Notes: These are Corporate level Gender Core Indicators that are intended to apply to all focal areas and enable aggregation to report results. These GEF gender indicators were results of an extensive discussion among gender experts from all GEF Agencies and partners. We are aware of the limitation of these indicators, and each project should use additional gender responsive indicators that are applicable to its focal areas/sector and more towards measuring results on gender equality and women's empowerment, rather than only counting beneficiaries or process oriented questions. At the same time, there are some evidence that having relevant processes (e.g. having gender analysis, gender responsive indicators, etc) lead to stronger gender approach and project results. The general consensus among the gender experts and key council members were that these indicators are a good start for the GEF, which could be further strengthened over time, particularly by identifying additional focal area/sector specific indicators. The core gender indicators and focal specific gender indicators will be further reviewed and refined as necessary as activity under the Gender Equality Action Plan.