## Slide 1: Accessing the GEF & GEF Project Cycle
GEF Expanded Constituency Workshop
Colombo, Sri Lanka
March 17-18, 2015

## Slide 2
Country-driven
GEF Focal Area Strategies
Identifiable global benefits
Participation
Consistency with global Conventions
Scientific and technical merit
Financially sustainable and cost-effectiveness
Monitoring, evaluation, and lessons learned
Endorsed by the OFP
Catalytic and leveraging role
GEF Project Requirements

## Slide 3
GEF project types by Grant Size:
Full-Sized Projects (FSPs): GEF grant > $2 million
Medium-Sized Projects (MSPs): GEF grant < $2 million
Enabling Activities (EAs): GEF grant is capped by respective focal area threshold:
  Biodiversity (NBSAP up to $250K, 6th National Report to CBD up to US$30K, 3rd National Report on Cartagena Protocol up to US$20K)
  Climate Change (National communications up to $500K, BUR up to US$ 352K)
  Land Degradation up to $150,000
  Chemical and Waste (MIA $200K; Persistent Organic Pollutants NIP $250K; and ASGM NAP=$500K)
Programmatic Approach (PA)
Small Grants Program (max $50,000)
MIA=Minamata Convention Initial Assessment
ASGM NAP = “Artisanal and Small Scale Gold Mining” National Action Plan
How we fund? GEF’s Grant Schemes

## Slide 4
Council approval of Work Program*
CEO endorsement of project
GEF Agency approval of project**
Project implementation and continues to completion***
* Work Program consists of PIFs cleared by the CEO
** GEF Agency approval of project signifies start of project implementation
*** Project completion follows terminal evaluation and financial closure
GEF Project Cycle

## Slide 5
One-step approach, preferred:
  Final MSP request and project document submit to the Secretariat for CEO approval, on a rolling basis.
  As needed, a PPG of up to $50,000 can be requested with MSP submission.
Two-step approach, only if required:
  Submission of a PIF with PPG request, if needed
  Submission of a final MSP document plus a MSP Approval Request for CEO approval
Medium-sized Project Cycle

## Slide 6
Enabling Activities follow two paths:
  Direct Access (follow direct access policy – applies the World Bank Operations Policies and Procedures):
    Country applies directly to the Secretariat for funding
  Regular procedures :
    Country works with a GEF Partner Agency to access funding.
Enabling Activities Project Cycle

## Slide 7
The new programmatic approach: approved by Council approval in the October 2014 Council meeting.
Steps include:
  Council approval of a Program Framework Document (PFD) included in a work program;
  CEO endorsement of fully prepared child projects under the program
Programmatic Approach Cycle

## Slide 8
Key document: Program Framework Document (PFD).
  All child projects under the Program have to be submitted for CEO endorsement by a deadline (or Program Commitment Deadline) agreed by relevant stakeholders during the preparation of the program concept or PFD.
  Child projects can apply for project preparation funding through submission of a PPG Request.
Features of a Program

## Slide 9
FSP = Full-Sized Project
MSP = Medium-Sized Project
EA = Enabling Activities
PA = Programmatic Approach
MIA=Minamata Convention Initial Assessment
ASGM NAP = “Artisanal and Small Scale Gold Mining” National Action Plan
PIFs = Project Identification Form/concept of a project
PFD = Program Framework Document
PPG = Project Preparation Grant
Acronyms

## Slide 10: .
Thank you for your attention!
Questions?
Lily Uy Hale (Lhale@thegef.org)
Sr. Operations Officer
Operations and Business Strategy
GEF Secretariat