## Slide 1
Senior Evaluation Officer
GEF Independent Evaluation Office
Georgia
June 2015
Evaluation in the GEF and
Training Module on
Terminal Evaluations
GEF Expanded Constituency Workshop
Baljit Wadhwa

## Slide 2: Overview
Evaluation in the GEF:
Monitoring and Evaluation in the GEF
GEF Independent Evaluation Office (IEO)
GEF M&E Policy 2010
Training Module on Terminal Evaluations

## Slide 3: M&E in the GEF
Two overarching objectives:
Promote accountability for the achievement of GEF objectives through the assessment of results, effectiveness, processes, and performance of the partners involved in GEF activities.
Promote learning, feedback, and knowledge sharing on results and lessons learned among the GEF and its partners as a basis for decision making on policies, strategies, program management, programs, and projects; and to improve knowledge and performance.

## Slide 4: Separate reporting lines for Monitoring (through Secretariat) and Evaluation (through IEO)
GEF Council
Agency evaluation units
GEF Independent Evaluation Office
GEF Secretariat
Agency GEF coordination units
GEF projects and programs
Annual evaluation reports
Overall Performance Study
(to Assembly)
Annual Work Program
and Budget
Annual Monitoring Report
Evaluation Management Response
Programming documents and indicators
Results Based Management
Project and Program Implementation Reports
Agency Portfolio Reports
Project documents with M&E plans
Project and Program
evaluations
Corporate evaluations
Project and Program
Independent evaluations
Project and Program Implementation Reports
Project and Program monitoring documentation
Terminal evaluations

## Slide 5: GEF Independent Evaluation Office
Mission:
Enhance global environmental benefits through excellence, independence, and partnership in monitoring and evaluation.
Functions:
Independent GEF Evaluation
Normative function
Oversight function
Knowledge sharing and dissemination
Brief history:
1996 — Initially established as an M&E unit within the GEF Secretariat
2003 — The M&E unit was made independent of the GEF Secretariat
2005 — The unit was renamed as GEF Evaluation Office
2013 — The office was renamed as GEF Independent Evaluation Office
Notes: Independent GEF Evaluation: The main function of the IEO is to independently evaluate the GEF’s efficiency, effectiveness, relevance, impact, and sustainability.
Normative function: IEO sets minimum monitoring and evaluation standards within the GEF to ensure improved and consistent measurement of the GEF results .
Oversight function: IEO provides quality control for the minimum requirements of monitoring and evaluation practices in the GEF, in full cooperation with relevant units in the GEF Agencies, and tracks implementation of Council decisions related to evaluation recommendations.
Knowledge management and dissemination function: IEO supports knowledge sharing and follow-up of evaluation recommendations. It participates in the development and maintenance of a comprehensive knowledge system based on evaluation findings and lessons.

## Slide 6: GEF IEO Stakeholders

## Slide 7: Types of Evaluations
Project Evaluations | Program Evaluations | Country Level Evaluations
Impact Evaluations | Cross-cutting and thematic evaluations | Process and performance evaluations
Ad-hoc Reviews | Overall Performance Studies (OPS) | Special Studies
Different TORs, scopes, frequency, audiences , methodologies

## Slide 8: GEF IEO Dissemination and Knowledge Management

## Slide 9: GEF IEO GEF-6 Work Program
Implementation of GEF M&E Policy
Evaluation Program adjusts to evolving GEF priorities
GEF IEO has started consultation to define the GEF-6 evaluation program
Reporting to the GEF Council
Participation in the GEF Country Support Program
Overall Performance Studies — replenishment process (every 4 years)
Active participation evaluation communities (UN/MDBs/other)

## Slide 10: The GEF M&E Policy
Defines the concepts, role, and use of monitoring and evaluation within the GEF
Defines the institutional framework and responsibilities
Indicates the GEF minimum M&E requirements covering:
  Project design
  Application of M&E at the project level
  Project evaluation
  Engagement of Operational Focal Points in M&E
Current M&E Policy: Approved by GEF Council in November 2010

## Slide 11
Training Module on
Terminal Evaluations

## Slide 12: Introduction
Purpose of this module is to:
  Discuss importance and utility of terminal evaluations
  Characteristics of a good terminal evaluation
  Exercise on pre-requisites for preparing a good terminal evaluation
    What needs to be done during project preparation and implementation
      When a project is prepared
      When a project is implemented
    What needs to be done during preparation and delivery of a terminal evaluation
      When a terminal evaluation is planned
      When a terminal evaluation is conducted
      When a draft report is prepared

## Slide 13: Importance and Utility of Terminal Evaluations
Source of information on project
  Results: Outputs, outcomes and progress to impact
  Implementation, execution, and project cycle related information
  Project finances including co-financing
  Recommendations and Lessons for the future
GEF M&E Policy (2010): Minimum Requirement 3
  Terminal evaluations mandatory since 1995
  For full-size projects required, encouraged for MSPs

## Slide 14: Importance and Utility of Terminal Evaluations contd.
Reporting at the project portfolio level (APR, AMR)
Input to other evaluations
STAR’s performance index
About 1000 terminal evaluations completed so far.
Terminal evaluation may be accessed at:
  GEF website: http://www.thegef.org/gef/gef_projects_funding
  Through PMIS

## Slide 15: Characteristics of a Good Terminal Evaluation
GEF IEO criteria for terminal evaluations quality:
  Outcomes
  Consistency and comprehensiveness
  Sustainability
  Lessons and recommendations
  Project finances
  M&E
Other characteristics of good terminal evaluations:
  Transparency and timeliness
  Candor
  Balance
  Utility
Question – is good terminal evaluation and good project performance the same?
Terminal Evaluation Guidelines are available at: http://www.thegef.org/gef/Guidelines%20Terminal%20Evaluations
Notes: Quality: Comprehensive; Consistent; Truthful and Candid; Precise; Timely; Useful

## Slide 16: Examples of Good Terminal Evaluations
Links to examples of good terminal evaluations
  GEF ID #394: http://www.thegef.org/gef/project_detail?projID=394
  GEF ID #1599: http://www.thegef.org/gef/project_detail?projID=1599
  GEF ID #1188: http://www.thegef.org/gef/project_detail?projID=1188
  GEF ID #1348: http://www.thegef.org/gef/project_detail?projID=1348

## Slide 17
You will be asked to think about what needs to be done to facilitate preparation of a good terminal evaluation:
  At different stages of terminal evaluation preparation
  At project preparation and implementation
Each group will discuss the requirements at each of these steps and will record their joint responses as bullets in the response sheet provided to them.
After all stages have been discussed by the groups, one of the groups will present its response for a stage, others may add if their group had an additional bullets not yet covered. Each stage will be presented by a different group.
We will end with a summary that pulls the discussion together
Exercise: Pre-requisites for preparing a good terminal evaluation

## Slide 18: First Discussion: What needs to be done during project preparation and implementation?
1 A. What needs to be done during the project preparation stage?
  Development of M&E plan
  Tracking tools
1 B. What needs to be done during the project implementation?
  Implementation of M&E plan
  Gathering of data on tracking tools

## Slide 19: Second Discussion: What needs to be done during preparation and delivery of a terminal evaluation?
Consider a situation where a project is about to be complete within one year. What needs to be done at different stages of terminal evaluation preparation to ensure that it leads to a good quality evaluation:
  2 A. Commissioning of the terminal evaluation
  2 B. Conduct of the terminal evaluation
  2 C. Finalization of the terminal evaluation

## Slide 20: Short Presentations by Stages
Presentation on group discussion
Summary