## Slide 1
Ms. Anna Viggh
Senior Evaluation Officer
22 September 2015
Evaluation of the
GEF Civil Society Organizations (CSO) Network

## Slide 2: Introduction
GEF IEO has begun consultations to inform the Evaluation of the GEF CSO Network.
Today’s presentation includes a brief overview of:
  CSO Network History
  Purpose of the CSO Network
  Membership and Structure
  Evaluation Objectives
  Proposed Methods/Tools
  Identified Limitations
  Knowledge Management & Communication Plans
  Management of the Evaluation
  Time Frame
Approach Paper was circulated with the GEF Partnership and is currently being finalized. Final will be posted on IEO website.

## Slide 3: The GEF CSO Network History
From its inception, the Pilot Phase, CSOs are acknowledged as critical stakeholders in the GEF.
Formalized and systematic consultations became a part of the restructured GEF, including mention in the Instrument of the importance of CSO participation (Para 5) and ability to act as executors (Para 28).
GEF restructuring resulted in a process of accreditation by the GEFSEC and semi-annual consultations amongst the Network and with Council, which are in still in place today.
Any accredited NGO was thus automatically a member of a “GEF NGO Network”. Council replaced the accreditation with a membership system (2009) to be operated by the Network itself in a similar manner with member CSOs eligible to attend Consultations and Council/Assembly meetings

## Slide 4: The GEF CSO Network Purpose
Members of the Network are focused on influencing Council proceedings and facilitating participation of NGOs in the Council, NGO Consultations and Program implementation.
The Network has developed a Vision, Mission and Objectives (v.2014):
Vision: “A dynamic civil society influencing policies and actions at all levels to safeguard the global environment and promote sustainable development.”
Mission: “To strengthen civil society partnership with GEF by enhancing participation, contributing to policy and stimulating action.”
Objective 1: To enhance the role of civil society in safeguarding the global environment
Objective 2: To strengthen GEF Program implementation through enhanced partnership with civil society
Objective 3: To strengthen the GEF NGO Network Capacity

## Slide 5: The GEF CSO Network Membership
The Network membership is currently comprised of 466 member CSOs. Of these:
      189 are in the Africa Region representing 37 countries;
      113 in Asia and the Pacific representing 32 countries;
      79 in Europe representing 27 countries; and,
      85 in the Americas representing 24 countries
Chart: CSO Network Membership
| Africa | Asia | Europe | Americas
Number of CSOs | 189 | 113 | 79 | 85

## Slide 6: The GEF CSO Network Structure and Governance
The structure of the Network has come about as a result of self-regulating initiatives,
Governance
Outreach
Strategy
Management
GEF-Related Conventions
Central Focal Point
16 Regional Focal Points
3 Indigenous People’s Representatives
Central Africa
Eastern Africa
Northern Africa
Southern Africa
Western Africa
Pacific
South Asia
North East Asia
South East Asia
West Asia
Caribbean
South America
Mesoamerica
North America
East Europe and Central Asia
Europe
Asia and Pacific
Africa
Americas
Coordination Committee

## Slide 7: GEF CSO Network Evaluation (2005)
Independent Review of the GEF NGO Network was presented to GEF Council in October 2005.
Conclusions:
  Model of NGO engagement at that time (both regional and country-level) was ineffective
  Network lacked a long term vision
  GEFSEC and Council had no long-term strategy for engaging the Network
  Insufficient Resources and a need for capacity building were major obstacles
  Secretariat, Council, Agencies and NGO community have a vested interest to re-energize the Network
Recommendations:
Increase the network’s accountability and effectiveness by strengthening the network’s management, increasing accountability in the application of the network’s Guidelines, re-focusing the accreditation process, and strengthening outreach to NGOs;
Establishing an active partnership between the NGO Network and the GEF Secretariat and Council; and
Providing support, financial and otherwise, to build the network’s capacity.

## Slide 8: Evaluation Objectives
Building on the 2005 review, this evaluation will answer the following key questions:
    To what extent is the CSO Network meeting its intended goals and strategic objectives and adding value to the GEF Partnership and its membership?
    How are Network features contributing to the effective and efficient functioning of the Network?
    What are the implications for the next phase of the development and evolution of the CSO network?

## Slide 9: Literature Review
The increase in number and influence of CSO networks worldwide post the 1990s have allowed for their activities to be the subject of greater scrutiny.
There is a growing body of literature on network formation, development, capacity building and evaluation. Evaluators have begun to develop frameworks for understanding networks using a mix of methods and tools:
Pre-Evaluation Phase entailed beginnings of review of the literature on networks and their evaluation.

## Slide 10: Key Questions (1)
Key Evaluation Questions | Network Elements | Example Evaluation Questions | Information Sources | Possible Approaches
Is the CSO Network meeting its intended goals and strategic objectives and adding value to the GEF partnership and its members? Network Objectives as set by the GEF Council: Preparing for and reporting on the GEF Council meetings and NGO Consultations to the wider CSO community at the national, regional & international levels Network Objectives as set by the CSO Network: To enhance the role of civil society in safeguarding the global environment To strengthen global environmental policy development through enhanced partnership between Civil Society and the GEF To Strengthen the GEF NGO Network Capacity | Connectivity | What GEF-relevant information (knowledge products, presentations, reports, etc.) is flowing through the Network to its membership and other stakeholders? | Network Documents Data / Results from Surveys, Interviews, and other primary sources (e.g. workshops) | (Online) Self-Assessment Interviews and Focus Groups/Focused meetings with key stakeholders Cost / Level of Effort Overview Assessment Social Network Analysis
 | Credibility | Are the Network’s objectives still relevant? To what extent has the Network aligned with GEF goals on gender mainstreaming and indigenous peoples’ inclusion? Has the CSO Network contributed to shaping the GEF agenda (getting new issues on the GEF agenda, policies incorporated by the Council)? | Council and GEF SEC Documents Network Documents Non-GEF CSO Networks | Document review Interviews and Focus Groups/Focused meetings with key stakeholders Surveys (Online) Self-Assessment Comparative analysis with other networks
 | Capacity | How are Network members adding value to one another’s work, i.e. achieving more together than they could alone? Are there clear signals of development of CSO/member capacity? | Data / Results from Surveys, Interviews, and other primary sources | Interviews and Focus Groups/Focused meetings with key stakeholders Surveys (Online) Self-Assessment
 | Progress towards Results | Are there clear signals of influence on GEF policy and program implementation? Can a case be made as to Network contribution? Has the Network membership monitored the implementation of GEF portfolios and policies at the country level? | Council and GEF SEC Documents Network Documents | Document review Interviews and Focus Groups with key stakeholders Surveys (Online) Self-Assessment

## Slide 11: Key Questions (2)
Key Evaluation Questions | Network Elements | Example Evaluation Questions | Information Sources | Possible Approaches
How are the CSO Network’s features (governance, structure, membership, connectivity, etc.) contributing to its ability to meet its objectives | Connectivity | How effective and efficient are the connections the network makes? Are all members contributing, individually or through joint efforts, to network goals? | Network Documents Data / Results from Surveys, Interviews, and other primary sources (e.g. workshops) | (Online) Self-Assessment Interviews and Focus Groups/Focused meetings with key stakeholders Cost / Level of Effort Overview Assessment Social Network Analysis
 | Membership | Who participates in the Network and why? Are women’s, indigenous peoples’ and youth organizations represented? Has the Network assembled member organizations with the capacities needed to meet Network goals (experience, skills, and connections)? Is the process for Network membership transparent, effective, and efficient? Has it changed over time? What is the geographic distribution of membership in relation to GEF operations? What have been the trends in membership? | Council and GEF SEC Documents Network Documents Data / Results from Surveys, Interviews, Focused meetings with key stakeholders and other primary sources | Document review Social Network Analysis Surveys Meta-Evaluations Comparison to other Networks Visual Timeline (infographic Representation)
 | Structure | Has the Network and GEF Partnership adjusted to meet changing GEF needs and priorities? What infrastructure is in place for Network coordination and communications? Are these coordination and communication structures efficient and effective? Are lessons from similar networks (Adaptation Fund, GCF, CIF, etc.) used to inform the workings of the GEF CSO Network? | Membership Databases Council and GEF SEC Documents Network Documents | (Online) Self-Assessment Social Network Analysis Visual Timeline (infographic Representation) Document review

## Slide 12: Key Questions (3)
Key Evaluation Questions | Network Elements | Example Evaluation Questions | Information Sources | Possible Approaches
How are the CSO Network’s features (governance, structure, membership, connectivity, etc.) contributing to its ability to meet its objectives | Governance | Are the Network’s governance rules applied in a transparent manner? Is there a transparent conflict resolution process? Do Network members actively participate in Network elections? Do decision-making processes encourage members to contribute and collaborate? How dependent is the Network on a small number of individuals? (male/female disaggregated) Do governance structures take into consideration gender mainstreaming? | Council and GEF SEC Documents Network Documents Data / Results from Surveys, Interviews, and other primary sources | Document review Interviews and Focus Groups/Focused meetings with key stakeholders Surveys (Online) Self-Assessment Meta-Evaluations Comparative analysis with other networks
 | Resources | What is the level of financial and technical resources provided to the Network? Has the Network secured needed material resources? Is the Network adapting its business plan over time? How has the GEF partnership [GEF SEC, Agencies, OFPs, IEO, etc…] supported the work of the CSO network? | Network Documents Data / Results from Surveys, Interviews, and other primary sources | Document review Interviews and Focus Groups with key stakeholders
 | Capacity | Does the Network have the needed capacities to advance members’ skills & Network goals? | Data / Results from Surveys, Interviews, and other primary sources Network Documents | Interviews and Focus Groups/Focused meetings with key stakeholders Surveys (Online) Self-Assessment

## Slide 13
Decisions on methods and tools will be made on the basis of issues identified.
Evaluation activities will involve:
  Further document review
  Comparative analysis with other networks
  Meta-evaluation
  Select individual interviews with key stakeholders
  Focus group meetings with key stakeholders
  Survey (CSO Network members/non-members/GEFSEC/Agencies)
  Self-Assessment (Coordination Committee)
Possible Approaches

## Slide 14: Additional Stakeholder Involvement
Reference Group:
  Includes representatives from the GEF Secretariat, GEF Agencies, the CSO Network, and SGP. The Reference Group will:
    Share comment on the Approach Paper and drafts of the Report; identify & establish contact with individuals for interviews/focus groups and identify & facilitate access to information.
    10 individuals
Expert Peer Review Group:
  Consists of relevant evaluation specialists from GEF Agency Evaluation Office and the broader evaluation community.
  3 individuals.

## Slide 15: Limitations
Networks are inherently complex and dynamic systems which makes them difficult to evaluate.
Main limitations of this evaluation will be:
  Access to entirety of CSO Network (over 460 members, different regions/access/languages)
  Access to older and archived documents of the CSO Network
  Relatively short timeframe

## Slide 16: Knowledge Management & Communications
The CSO Network Evaluation will add to the growing body of literature on network evaluations and thus will be of broad interest to the evaluation community.
The IEO will disseminate information gathered at various points in the course of the evaluation with stakeholders.
Information sharing could take place through various platforms such as:
  Online stakeholder groups
  Webinars
  Published knowledge products

## Slide 17: Management of the Evaluation
The evaluation will be task managed by Ms. Baljit Wadhwa, Senior Evaluation Officer, leading a team comprising of GEF IEO staff and consultants.
Consultants are contracted to undertake specific elements which include peer review and analysis of data on the CSO membership, connectivity and network health though self assessments and/or social network analysis, etc.

## Slide 18: Time Frame
Phase | Evaluation Phase | Time Frame
1 | Pre-evaluation desk review, upstream consultations & Approach Paper | End of June 2015
2 | Further desk review; identification of data gaps; further methods selection; survey instrument | July – August 2015
3 | Application of appropriate methods/tools for additional data gathering and analysis Peer Review & Reference Group Consultation | September 2015 – January 2016 September 2015
4 | Triangulation, verification, gap analysis and preparation of Evaluation Report Draft Evaluation shared and discussed with Reference Group/ and stakeholders and edits finalized | January - April 15, 2016
5 | Final Evaluation shared with GEF Council Evaluation Conclusions & Recommendation presented at GEF Council meeting Knowledge products and dissemination activities | May 2016 June 2016 May - September 2016

## Slide 19: Questions and Feedback
We are looking for feedback on:
Survey Questions
Key Questions
Your Experience with the GEF CSO Network