## Slide 1: GEF Project Cycle
GEF Expanded Constituency Workshop
July 19 – 21, 2011
Monrovia, Liberia
Notes: <number>
GEF Expanded Constituency Workshop

## Slide 2: GEF Project Cycle
The GEF project cycle is a process involving many partners on the frontline: countries, GEF Agencies, GEF Secretariat, GEF Council, and partners.
Other important partners perform behind the scene functions:
Trustee who sets aside funds for projects, commits funds and transfer funds;
STAP who screens projects upstream and provides scientific guidance for the project or program;
Evaluation Office which evaluates completed projects and selected themes and undertakes annual performance reviews;
Convention secretariats, also provides guidance and comments on projects.

## Slide 3
The project cycle through the GEF partnerships
Trustee
STAP
GEF Assembly
Countries:
Political
FPs
GEF
Secretariat
GEF Agencies
•
UNDP
•
UNEP
•
World Bank
ADB
•
AFDB
•
EBRD
•
FAO
•
IADB
•
IFAD
•
UNIDO
Projects
Countries:
Operational
FPs
,
Convention
FPs
, other
gov
’
t
agencies, civil
society
Evaluation
Office
Conventions
Countries:
Convention
FPs
GEF Council
Countries:
Council
Members/
Constituencies
STAP
GEF Assembly
Countries:
Political
FPs
GEF
Secretariat
GEF Agencies
•
UNDP
•
UNEP
•
World Bank
ADB
•
AFDB
•
EBRD
•
FAO
•
IADB
•
IFAD
•
UNIDO
Projects
Countries:
Operational
FPs
,
Convention
FPs
, other
gov
’
t
agencies, civil
society
Evaluation
Office
Conventions
Countries:
Convention
FPs
GEF Council
Countries:
Council
Members/
Constituencies
Project review
Project Development
Project idea,
endorsement,
Project implementation,
Work Program
Strategic Guidance

## Slide 4: Project process
Project idea: 1 page
Project Concept: < 8 pages
Project Preparation: < 5 pages
Project document:

## Slide 5: Project cycle in the GEF
Project idea – Countries - NPFE
Project Concept – Agencies – PIF (template)
Project Preparation – Agencies – PPG (template)
Project document – Agencies – FSP or MSP (EA) (template)

## Slide 6: Features of the GEF-5 project cycle
PIF submitted on a rolling basis;
18 months preparation for FSP: begins from date of Council approval of the work program till CEO endorsement of the final project document;
12 months preparation for MSP: applies only to those MSPs that requested PPG; begins from date of PIF approval by CEO to approval of final project document by CEO;
Program Framework Document (PFD) for Programmatic Approaches (PA) can be submitted only for Council meetings, scheduled twice a year (May and November)

## Slide 7: GEF Project Cycle Steps (1)
Main steps for For Full-sized Projects FSP:
Council/Secretariat:
Council approval of the work program, consisting of PIFs cleared by the CEO;
CEO endorsement of the final project document.
GEF Agency:
Approval of the project by the GEF Agency and implementation start;
Completion of implementation, terminal evaluation and financial closure.

## Slide 8: Full-Sized Projects
* Work Program consists of PIFs cleared by the CEO
** GEF Agency approval of project signifies start of project implementation
*** Project completion follows terminal evaluation and financial closure

## Slide 9: GEF Project Cycle Steps (2)
Main steps For Medium-sized Projects:
Single-step approval:
CEO approval of final MSP document;
Agency’s own internal approval and implementation starts.
Two-step step approval:
If PPG requested, submit PIF for CEO approval;
CEO approval of final project document;
Agency’s own internal approval and implementation starts.

## Slide 10
Medium-Sized Projects
* Agency approves MSP after CEO approval of the project and starts implementation.

## Slide 11: GEF Project Cycle Steps (3)
For Enabling Activities (two paths):
Direct Access (follow direct access policy):
Country submits EA proposal for CEO approval;
CEO and country sign Grant Agreement and implementation starts.
Follow existing procedures of applying EA grant through Agencies:
Agency submits EA proposal for CEO approval;
Agency follows its own internal approval procedure and implementation starts.

## Slide 12
Expedited Enabling Activity
Grant Agreement signed between Government and GEF CEO**
National Agency completes implementation of EA and submits Report to Convention
GEF Agency completes implementation of EA and country submits Reports to Convention
GEF Agency approves EA following CEO approval***
GEF Agency submits proposal for CEO approval
National Agency submits EA proposal to GEF Agency
* GEF Secretariat will follow the World Bank procedures in approving the proposal with final target
of sending a Grant Agreement to the recipient country and to be signed between CEO and the country.
National Agency submits EA proposal for CEO approval*

## Slide 13: Review Criteria for FSP/MSP
Country eligibility and ownership
Global Environment Benefits
GEF Focal area strategy
Agency’s Comparative advantage
Resource availability
Project consistency
Project design
Project financing and co-financing (baseline)
Monitoring and evaluation; and
Agency’s responses to comments and reviews.

## Slide 14: Country Endorsement (by Country National Operational Focal Point)
All PIFs should have OFP endorsement when submitting to GEF for clearance (in case of FSPs) or approval (in case of MSPs requesting a PPG)
Projects in biodiversity, climate change, and land degradation focal areas follow STAR rules

## Slide 15: Agency Fee
For stand-alone projects, a 10% fee based on the GEF amount for the project (project grant + PPG);
Agency fees for Programmatic Approaches vary depending on the type of Agency submitting the PA:
Qualifying Agencies: 8%
Non-qualifying Agencies: 9%
In case of project cancellation, all unused fees or a specific percentage should be returned to GEF Trust Fund.*
* Reference to Council paper, “Proposal for Revising the Fee System” (GEF/C.23/8/Rev.1) for fee return guidelines.

## Slide 16: Programmatic Approaches
Two Types of programmatic approaches, depending on the type of GEF Agency submitting the program:
Qualifying GEF Agencies (QGA): those GEF Agencies meeting the criteria for delegated approval authority;
Non-qualifying GEF Agencies: those GEF Agencies not meeting the criteria, such programs can be submitted by a Program Coordination Agency (PCA).

## Slide 17: Role of STAP - Stand-alone Projects
STAP provides strategic scientific and technical advice to the GEF on the following:
FSPs:
Selectively screens PIFs received from Agencies when submitted to GEF Secretariat;
Screens all PIFs cleared by CEO for work program inclusion; screening reports are posted on the GEF website together with PIFs in the work program.
MSPs:
selectively screens MSP PIFs.

## Slide 18: Role of STAP
Programmatic Approaches (similar to FSPs)
Selectively screens PFDs received from Agencies when submitted to GEF Secretariat;
Screens all PFDs cleared by CEO for work program inclusion;
Screening reports are posted on the GEF website together with PFDs in the work program.

## Slide 19
THANK YOU FOR YOUR ATTENTION!
GEF website:
www.thegef.org