## Slide 1: The Importance of the Midterm Review
A Case Study exercise from Mauritius

## Slide 2: The Importance of the Midterm Review from Agencies Point of View
UNDP-GEF Regional Technical Advisers often say to project teams,
“The Terminal Evaluation is important for the GEF to see what was achieved for their investment.
The Midterm Review is important for you – and for UNDP – because if performance is poor, we can still turn things around.”

## Slide 3: Questions about the Midterm Review (MTR)
What makes the MTR different from other reporting requirements?
Who benefits from the MTR and how?
How can the MTR catalyze change in a project?
What questions should be asked by the MTR?
Beyond the scope of a single project, how can MTR reports be used?
A case study will help us answer these questions...

## Slide 4: The Management and Protection of the Endangered Marine Environment of the Republic of Mauritius
GEF funded
UNDP implemented
Medium-Sized Project
Focal area: Biodiversity
GEF Strategic Priority: SP1 (Protected Areas)
Total GEF Grant: US$ 1.00 million
Total Co-financing:
  US$ 3.36 million at CEO Approval stage
  US$ 3.0 million effectively mobilised
A Case Study from Mauritius

## Slide 5: Background – Project Summary & Context
Applied a two-prong approach:
  Develop an enabling policy and institutional framework for sustainably co-managed MPAs throughout the Republic; and
  Develop innovative co-management arrangements for MPAs and adapt them at a representative demonstration site in Rodrigues.
Faced many complexities:
  the two components were implemented by different national entities
  collaborative co-management was new and innovative in the country
  many partners were involved: Government, local communities, private sector
  Active management of MPAs was new to the country at project start and there were no MPAs on Rodrigues Island
Required a significant amount of technical know-how to reach its targets
A Case Study from Mauritius
Notes: The two components were implemented by different national partners, more or less independently from each other.
This ‘disjunction’ was reinforced by the gradual decentralisation process taking place at the national level, and which conferred more administrative and governance autonomy to Rodrigues. When the PRODOC was approved, the Rodrigues Regional Assembly had just been created and provided with a strong mandate for decentralised management of the Island as a whole (economy, resources, services etc.).
The demonstration component of the project was based on Rodrigues, the second largest island in the Republic, but with a much smaller size, population and a lower development level. A new MPA was successfully established from scratch on Rodrigues.

## Slide 6: Background – Project Milestones
GEF CEO Endorsement August 2003
ProDoc Signature January 2004
First disbursement 2005
Original Closing June 2008
Actual Closing Sept 2012
A Case Study from Mauritius
Notes: Concept Approval = PIF-equivalent

## Slide 7: Background – Annual Disbursement
Annual Disbursements by Funding Source
Peak implementation
A Case Study from Mauritius
Notes: “Total” includes UNDP-managed funds only, which also includes government cost-sharing

## Slide 8: Background – M&E Milestones
First PIR Sept 2005
Midterm Evaluation June 2008
Final PIR/Terminal Evaluation Sept 2012
2003
2004
2005
2006
2007
2008
2009
2010
2011
2012
Effective implementation period
Period of most intense implementation
A Case Study from Mauritius

## Slide 9: The MTE – “A turning point”
Rated the project Marginally Unsatisfactory (MU)
Revealed the reasons for delays, and solutions
Provided specific and detailed recommendations
Findings and recommendations were embraced by project team, UNDP, other partners
  Continuation of the project made conditional on the implementation of the recommendations
Described as “a turning point” by the TE report
A Case Study from Mauritius
Notes: From TE report (page 24)
The Mid Term Evaluation conducted in 2008 seems to have had an important influence over the project performance during subsequent years. Many of its recommendations were implemented, in particular two significant ones: (i) the establishment of a new position within the project to support the work of the PMU and provide training and capacity building of the existing personnel, and (ii) to finalize the M&E plan for the project, which resulted in an adjusted Logical Framework. As demonstrated in subsequent PIRs (2009, 2010, and 2011), implementation in Rodrigues accelerated greatly as a result, and delivered a main project target for Outcome 2: the creation of the “South East Marine Protected Area” (SEMPA), gazetted in 2009.
The years of 2010 and 2011 saw further consolidation of project outputs for Outcome 2, including the successful zoning of SEMPA, and the development of key planning documents for successful management including several studies and the development of SEMPA’s Management Plan. In 2011 and early 2012, rapid implementation of various components for Outcome 1 also took place.

## Slide 10: Notable Findings of the MTE
Difficult to achieve Outcome 1 in the political, administrative, legal context (decentralisation implying new roles and mandates)
  needs to be redesigned and focused on MPAs, to maintain relevance
  activities not started
Design of Outcome 2 “highly relevant”
  “generally high” levels of commitment, enthusiasm
  some outputs with good progress, e.g. on Rodrigues in developing a co-management approach to MPA establishment and management
Delays in implementation have meant that it was too early to see any real achievements under the Outcomes
  Only 3 of the 10 outputs were sufficiently advanced to show progress; rated MS
  Large backlog of activities not yet undertaken
  Significant under-expenditure; advantageous in that it would allow for an adjustment of the budget to take on additional assistance for the final phase
Lack of working examples in country required boosting capacities at all levels for managing a project of this size
  In particular full time Technical Advisor with MPA know-how was not in team
A Case Study from Mauritius

## Slide 11: How did the MTE catalyze the change?
MTE was thorough and specific in raising flags about the project’s poor performance and trends
Outlined actionable and concrete recommendations:
  to establish a new position within the project to support the PMU, and provide training and capacity building; bring in outside expertise on MPAs
  to finalize the project’s M&E plan and review the Logical Framework
  to undertake a comprehensive training needs assessment
  to revise activities under Outcome 1 and prepare a workplan
  to initiate the process for preparing the draft management plan for SEMPA
  Revealed ways in which the country could drive a turnaround in the project, e.g. stressed the need for political commitment
These and other recommendations were immediately acted on by Government partners, UNDP and project team, bringing about major improvements in implementation
A Case Study from Mauritius

## Slide 12: After the MTE...
Logframe streamlined and made more ‘results-oriented’ with clearer and SMART’er indicators
Systematic tracking of MTE management response
Consolidation of key project outputs
  successful zoning of the MPA and its enforcement
  development of key MPA planning documents
  implementation of key activities in Component 1, which had seen no progress till the MTE.
Multi-year budgetary planning enforced
New Chief Technical Adviser engaged
Marginally Satisfactory (MS) overall rating from TE, with some Highly Satisfactory (HS) components
A Case Study from Mauritius
Notes: Lesson from the TE report:
“Mid-Term Evaluations can be Critical to Place a Project Back on Track. As has been mentioned in previous sections, the MTE had a crucial impact and is acknowledged as a decisive influence to put the project back on track. The two main reasons why this happened are the following: (i) recommendations were sharp, actionable, and very concrete; and (ii) these recommendations were followed up immediately by UNDP. “

## Slide 13: Highlights of the Project’s Results
Establishment of the South-East Marine Protected Area (SEMPA) across 4,200 ha
Improved management effectiveness of SEMPA (METT score rose from 7% to 81%)
Developed innovative co-management arrangements for marine PAs
Increased communities’ sense of ownership of the MPAs; approximately 50 families are now directly involved in MPA activities
Supported the recruitment of fishermen as Field Rangers, offering an alternative livelihood
Reduced pressures on marine resources; independent monitoring confirms that MPA zones are adhered to and infractions are reported and penalized
A Case Study from Mauritius

## Slide 14: Questions about the Midterm Review (MTR)
What makes the MTR different from other reporting requirements?
Who benefits from the MTR and how?
How can the MTR catalyze change in a project?
What questions should be asked by the MTR?
Beyond the scope of a single project, how can MTR reports be used?

## Slide 15: Answers...
What makes the MTR different from other reporting requirements?
  independent and holistic assessment
  gives a fresh, unbiased view of the project
  identifies potential for improvement
  produces actionable, realistic, results-oriented and concrete recommendations
  completed when the project still has time to recover and improve
  presents a learning opportunity for all involved

## Slide 16: Answers...
Who benefits from the MTR and how?
  all stakeholders – it could be the difference between make-or-break
  the project team – MTR as a learning exercise for improving performance and achieving results
  the Government – providing specific policy guidance, promoting efficiency and informing decision-making
  the project partners – rethinking their role and contribution to project results
  the GEF agency – as a tool for institutional learning and identification of needed solutions

## Slide 17: Answers...
How can the MTR catalyze change in a project?
  Reviewing project design/assumptions in light of changed circumstances and adjusting design accordingly
  inspiring the project team and partners through recognition of the project’s relevance
  proposing concrete and actionable recommendations
  outlining how those recommended changes have the potential to improve the project’s results

## Slide 18: Answers...
What questions should be asked by the MTR?
  Are there signs of advances towards the outcomes?
  What progress does the midterm GEF Tracking Tool show?
  What challenges are causing delays?
  What has changed in the context?
  Is the project still relevant?
  Are there new opportunities?
  How can the challenges be overcome?
  Is it feasible to complete with the remaining resources and the existing context?

## Slide 19: Answers...
Beyond the scope of a single project, how can MTR reports be used?
  Learning: to reveal trends across a portfolio from which overarching lessons can be extracted and change thereby promoted
  Results: to summarize mid-point results, which can be aggregated at the portfolio level
  Knowledge: to advance our understanding of the hurdles faced by projects during implementation